## Instructions
Stakeholder List and RACI Instructions
Step 1: Identify your Stakeholders
The first step in your stakeholder analysis is to brainstorm who your stakeholders are. As part of this, think of all the people who are affected by your investment, who have influence or power over it, or have an interest in its successful or unsuccessful conclusion. Remember that although stakeholders may be both departments and people, ultimately you can only communicate with individual people. Make sure that you identify the correct individual stakeholders within the department.
Step 2: Prioritise your Stakeholders
You may now have a list of people and areas that are affected by your investment. The sheet Stakeholder List is a proposal on how to document this list. This can be adapted to the investment's particular needs as long as required information is documented: - Enter the names of the various stakeholders - Enter the department / area they represent - Select the stakeholder role 1 (client, participant, oversight, advocate SME or receiving investment manager) - Select the stakeholder role 2 (Active or Passive) - Select the Priority level (1 – 4, based on stakeholder's influence and importance of their actions) - Select Communication preference (verbal, written, verbal & written) - RECOMMENDED NOT MANDATORY - Enter Reporting Preference (e.g. milestones, project report, customised, none) - RECOMMENDED NOT MANDATORY - Enter a Delegate name for the Stakeholder if they are not available (mandatory only for priority 4 and 3) - Provide any further Comments about the stakeholder (e.g. Is this stakeholder interested in the outcome of the investment or in the investment implementation process? Is this stakeholder having a positive (investment seen as a benefit or a known mandatory requirement) or a negative (investment seen as a "hindrance") influence? Is this stakeholder able to provide guidance? How far is the stakeholder involved in issue resolution?) Please take into account sensitivity of the Stakeholder List information. It should be confidential within the investment and some key staff in the investment if it is to be used to its full value. Once the investment is formally closed, please make sure that all stakeholders have been informed.
Step 3: Complete the RACI Chart
Allocate major project management activities to roles / individuals. Do not enter single tasks required to reach the objectives as these are tracked in the milestone plan. - Draft the RACI during the initiation phase to identify key roles, high level sponsorship and forums required to oversee the initiative. - Complement the RACI during the planning phase with a detailed organisation chart for the investment and with governance and forums to be documented in the Change Management Plan. - During execution, changes to the RACI must be formally approved via the change request process. - During closure, the RACI will outline clear ownership and handover between the project and receiving business and operations leads.

## Stakeholder List
STAKEHOLDER LIST | [8 empty] | Client | Active | 4 | Verbal
Purpose: | Identify all the stakeholders affected by the outcome of the investment, define attributes such as role, interest, priority etc. | [7 empty] | Participant | Passive | 3 | Verbal & Written
Investment Name and dbClarity ID: | <project name> | [7 empty] | Oversight |  | 2 | Written
Stakeholder Name | Area | Role 1 | Role 2 | Priority | Communications | Reporting | Delegate | Comments | Advocate
Enter the name of the Stakeholder. | Enter the name of the business area the Stakeholder represents. | Select Role type from drop down list: - Client: End user / Impacted area etc. - Participant: Key Investment Member - Oversight: Governance over the investment (e.g. Compliance, DCO, CAO, JET Council etc.) - Advocate: Driver of the investment - SME: Subject Matter Expert. | Select 2nd Role type from drop down list: - Active: who can affect or determine a decision or action - Passive: who are affected by decisions or actions by others. | Please see separate explanation box. | Select the preferred communication type for the Stakeholder from drop down list: - Verbal: calls / meetings / workshops - Written: Reports / emails / presentation - Verbal & Written: a combination of the above. | Provide the reporting information the Stakeholder will receive, e.g. milestones, project report, customised (e.g. for regulators), none. | Enter a delegate name to contact if the Stakeholder is unavailable for priority 4 and 3 Stakeholders (optional for priority 2 and 1) DISCLAIMER: If not specified otherwise, the delegate shall be identified depending upon the context | Provide any further comments about the Stakeholder, e.g.: Is this stakeholder interested in the outcome of the investment or in the investment implementation process? Is this stakeholder having a positive (investment seen as a benefit or a known mandatory requirement) or a negative (investment seen as a "hindrance") influence? Is this stakeholder able to provide guidance? How far is the stakeholder involved in issue resolution? | SME
SteerCo
King, John | Board | Participant | Active | 4 | Verbal & Written | Customized deck |  | Responsibility of delegation lies with …
Program Management
Miller, Alan | Integration Office | Participant | Active | 4 | Verbal & Written |  |  | Responsibility of delegation lies with …
Sponsors
Legal
Looney, George | CAO | Advocate | Active | 4 | Verbal & Written | Customized deck |  | Responsibility of delegation lies with …
Regulatory Affairs Office
Rules, Ronny | CRO | Oversight | Active | 4 | Verbal & Written |  |  | Responsibility of delegation lies with …
Stakeholders
Human Resources
People, Paul | CAO | Oversight | Passive | 4 | Verbal & Written | Customized deck |  | Responsibility of delegation lies with …
Finance
Money, Minny | CFO | Participant | Passive | 4 | Verbal & Written | Indirectly via customized deck |  | Responsibility of delegation lies with …
PMO
Mo, Peter |  | Participant | Active | 3 | Verbal & Written | Project report |  | Delegation within the PMO team
Workstream 1
It-Done, Gert |  | Participant | Active | 3 | Verbal & Written | Project report
Subworkstream 1.1
Paket, Wolfgang |  | Participant | Active | 3 | Verbal & Written | Project report
Subworkstream 1.2
Paket, Dieter |  | Participant | Active | 3 | Verbal & Written | Project report
Workstream 2 | N.B. The section "Area" is used in the following to list the name of the project led by the corresponding lead (DB reference is dbClarity, PB reference is PBDemand ) | [6 empty] | N.B. Subworkstreams consistsing of a single project are not listed in the following, unless the corresponding project leads do not coincide with the subworkstream leads
Wok, Wei-Chi | Audit | Oversight | Passive | 3 | Verbal & Written | Customized deck/rep. | N/A | Audit is not part of the program
| Legend: | Text | Mandatory information
|  | Text | Recommended information only
Priority:
  4 = High influence, high importance: stakeholders who stand to lose or gain significantly from the investment and whose actions can affect the investment's ability to meet its objectives.
  3 = High influence, less importance: stakeholders whose actions can affect the investment's ability to meet its objectives, but do not stand to lose or gain much from the investment.
  2 = Low influence, high importance: stakeholders who stand to lose or gain significantly from the investment, but whose actions cannot affect the investment's ability to meet its objectives.
  1 = Low influence, less importance: stakeholders who do not stand to lose or gain much from the investment and whose actions cannot affect the investment's ability.
Important information
ToDos:
- Fill stakeholders business area
- Fill delegate DB (if any)
- Fill PB Audit (after Kick-Off in Bonn has taken place - KW05)
- Fill Box&Stop members (List from central PMO - Delivery pending)

## RACI
RACI: Responsible - Accountable - Consulted - Informed
Purpose: | BACKGROUND: Merge the two legal entities Deutsche Bank PGK AG and Postbank AG into a new legal entity called DB Privat- und Firmenkunden AG. PROBLEM STATEMENT: At the forthcoming deadline for the merger first step the operations of the new legal entities shall be ensured; The Day-1 Readiness shall therefore be sought tactical solutions involving both Deutsche Bank PGK AG and Postbank AG. OBJECTIVES and MILESTONES: Ensure D1 Readiness of business, IT supported processes and reporting requirements for the new legal entity via tactical solutions. These requirements are defined by the Business partners and mainly based on regulatory requirements set by, or agreed with, the Joint Supervisory Team (JST) and other regulators. Initial target date for the merger of the legal entities is Q2 2018.
Program Name and dbClarity ID: | Aquila Day-1 Readiness, dbClarity ID: INV66789
Project Management Activity | Description | JET Council | Aquila SteeCo | Integration Office | Program Management | ‘One Bank’ Oversight Team | SteerCo | Integration Office | Governance Body 3 | GB 4 | GB 5 | GB 6 | GB 7 | GB 8
Allocate major project management activities to roles / individuals. Do not enter single tasks required to reach the objectives as these are tracked in the milestone plan. | Explanation of the activity. | [10 empty] | E.g. Subject Matter Expert, Subworkstream Lead etc.
Senior Management Level
Strategy of integration program at the highest level | Define strategic direction for the integration program | Informed | Accountable |  |  |  | Accountable | Responsible | Consulted | Informed | Responsible | Responsible
Development and approving success factors at the highest level | Develops and approves recommendations regarding the program budgets, -objectives and -measures of success | Informed | Accountable |  |  |  | Accountable | Responsible | Consulted | Informed | Responsible | Responsible
Tracking initiative | Monitors integration progress, address and mitigates critical topics, monitor budget and timeline, ensure stakeholder commitment | Informed | Accountable |  |  |  | Accountable |  | Consulted
Management program | Manage overall program as well as cross-subworkstream risks, issues, and dependencies |  | Informed | Informed | Informed | Informed |  |  | Accountable | Responsible | Responsible
Tracking program | Track and evaluates key activities / milestones on level including interdependencies and critical path for program, workstream status updates and program risks and issues along the dimansions time, scope and budget |  | Informed | Informed | Informed | Informed |  |  | Consulted | Accountable | Responsible
Reporting program | Report on program financials (CTB) and potential change requests regarding changes in scope / timing and financials |  | Informed |  | Informed | Informed |  |  | Accountable | Responsible | Responsible
2nd escalation instance (either 'One Bank' Lead or 'One Bank' OpCo for change management) | Provide guidance as 2st level of escalation and decide for a further escalation to SteerCo |  | Informed |  |  | Accountable |  |  | Accountable | Responsible | Responsible | Responsible | Responsible
SUBWORKSTREAM LEVEL
Ensure CGF compliance | Oversight the creation of the minimum standard documents as well es the transition between program phases |  |  |  |  | Informed |  |  | Accountable | Informed | Responsible | Responsible
Contribution to CGF compliance | Creation of CGF mandatory artifacts to ensure compliance with the CGF minimum standards |  |  |  |  | Informed |  |  | Informed | Informed | Accountable | Responsible | Responsible | Responsible
Tracking at the subworkstream level | Tracking of the progress at the subworkstream level | [7 empty] | Informed | Informed | Consulted | Responsible | Accountable | Responsible
Reporting at the subworkstream level | Report on a regular basis to the D1R leads and PMOs on the project status, potential risks and issues as well as dependencies | [7 empty] | Informed | Informed | Consulted | Responsible | Accountable | Responsible
Delivery artifacts and deliverables at the subworkstream level | Ensure the delivery of the artifacts and deliverables necessary to cover the subworkstream scope on time and in the required quality | [7 empty] | Informed | Informed | Consulted | Responsible | Accountable | Responsible
Coordination and alignment at the subworkstream level | Drive regulatory alignment jointly with Regulatory Affairs Office (schedule, prepare and conduct meetings) | [7 empty] | Informed | Informed | Consulted | Responsible | Accountable | Responsible
PROJECT LEVEL
Definition scope, milestones, timeline and budget at the project level | Define scope, milestones and timeline for the project implementation at the project level. Evaluation of the required ressources, their allocation on the project and estimation of cost of other sorts that will incur in the implementation | [7 empty] | Informed | Informed | Informed | Consulted | Consulted | Accountable
Tracking at the project level | Tracking of the project progress which shall be carried out and recorded by means of either dbClarity or PBdemand | [7 empty] | Informed | Informed | Informed | Informed | Consulted | Accountable
Reporting at the project level | Report on a regular basis to the leads on the project status, potential risks and issues as well as dependencies | [7 empty] | Informed | Informed | Informed | Informed | Consulted | Accountable
Delivery artifacts and deliverables at the project level | Ensure the delivery of the artifacts and deliverables necessary to cover the project scope on time and in the required quality | [7 empty] | Informed | Informed | Informed | Informed | Consulted | Accountable
Coordination and alignment at the project level | Drive coordination and alignment with the subworkstream leads of interest, with other project leads, in particular in case of dependencies, and with the regulatory bodies on topics relevant for the project | [7 empty] | Informed | Informed | Informed | Informed | Consulted | Accountable
Initiation change request at the project level | Initiate the change request procedure as described in the change request management document | [9 empty] | Informed | Consulted | Informed | Accountable
RACI Definitions
  Responsible: Those who do the work to achieve the objective. There is typically one role with a participation type of Responsible, although others can be delegated to assist in the work required.
  Accountable: Those who are ultimately accountable for the correct and thorough completion of the objective, and the one to whom Responsible is accountable. In other words, an Accountable must sign off (Approve) on work that Responsible provides. There must be only one Accountable specified for each objective. The person has Yes/No/Veto.
Consulted: Those whose opinions are sought; and with whom there is two-way communication.
Informed: Those who are kept up-to-date on progress, often only on completion of the objective; and with whom there is just one-way communication.
Important information
  JET Council tasks: to be listed
  Content sources : Aquila D1R guide, dbClarity reports
ToDos:
- Role and responsability Box&Stop team members